Ministry of Local Government, Rural Development & Cooperatives

Local Government Division

Local Government Engineering Department

Guidelines for Capacity Development Unit

Project Coordination Office

City Governance Project (CGP)

February 2018

Assisted by

Japan International Cooperation Agency-JICA

and

Urban Management Unit, LGED

Table of Contents

1.	Introduction	1

2.	Justifications	1

3.	Relevant issues of ICGIAP	1

3.1	Areas of Activity  Capacity Development Unit (CDU) established and formulated training program	1

3.2	Tasks of CDU	2

3.3	Composition of CDU	2

3.4	ToR of CDU	2

3.5	Action by	2

3.6	Time Schedule	2

3.7	Indicators	2

4.	Objectives	3

4.1	Objectives	3

5.	Relevant Organizations, Stakeholders and their role	3

5.1	PCO/PIU	3

5.2	Training providers	3

5.3	Administrative Reform Committee	3

6.	Necessary Tasks and Procedure	3

6.1	Formulation of CDU	3

6.2	Orientation workshop	4

6.3	Formulation procedure of training program	4

6.4	Schedule and Monitoring of Activity	5

6.5	Assessment of Capacity Development Program	5

6.6	Quarterly and final report on CDU activity	5

7.	Implementation Schedule	5

7.1	Formation of CDU	5

7.2	Formulation of Capacity Development Program	5

7.3	Monitoring	5

7.4	Assessment	5

7.5	Reports	6

Annex I	List of Training Provider	7

Annex II	Summary Sheet for Capacity Development Program	1

Annex III	Format for Proposal for Capacity Development Program	2

Annex IV	Format for Proposal for Training Activity	6

Annex V	Schedule of Capacity Development Program and Monitoring Sheet	1

Annex VI	Format for Assessment for Capacity Development Activity	1

Annex VII	Format for Quarterly Report	1

Annex VIII	Implementation Schedule	2

Annex IX	Sample Budget for implementation of the CDU	3

# Introduction

Rapid urbanization accelerated by industry led economic growth has been taking place in Bangladesh. Potential of economic growth in urban area is worthy of notice. There are 335 Local Government Institutions which cover 8% of total geographical area of Bangladesh and 30% of total population, while it accounts for 60% of total national growth. On the other hand, negative impact caused by the dramatic change in urban area is observed.  It is because the functions of municipalities and city corporations prescribed in Local Government (Pourashava) Act 2009 and Local Government (City Corporation) Act 2009 which are very relevant to the demand of city dwellers and urban development are not implemented in an appropriate manner.  In order to improve the public services provided by urban local governments, several urban development projects are/were implemented by LGD and LGED with financial assistance of different development partners and government own fund. Based on the experiences gained through implemented projects, effective activities for improvement of urban governance have been formulated as a program, and well accepted. The urban governance improvement programs have been implemented to ensure good governance of those urban local government institutions namely Pourashava for equal, social harmony and planned development.  Initiating urban governance improvement, LGD and LGED with financial support of JICA commenced a project named City Government Project (CGP) in 5 City Corporations.

# Justifications

Capacity development is one of essential activity to build inclusive city governance. At present, CCs have failed to conduct some of functions due to different reasons. One of the reasons is the capacity of officials. Since CC need to cover the functions given in CC Act with limited human resources and fund, CCs need to increase manpower, improve skills of officials, bring Kaizen to improve their work with minimal input and install equipment.

Different donors arrange several training programs for local government officials. The training is basically on the project basis; thus they are usually ad hoc in nature. Moreover, the training is not proactively formulated by CCs, and they are externally prepared. Officials will gain capacity on specific subject, which is often project activity oriented, through the training provided by the projects, and they may not always have the chance to upgrade skills and knowledge they need for their daily activities.

On the other hands, the needs for training towards officials are diverse, especially in CCs where the functions of town are differentiated from Paurashavas due to geographic location, economic activities, private sector activities, availability of NGOs and CBOs or the lifestyle of the general public. It may be necessary for local governments to formulate a training program according to the needs of resident’s officials and policies they independently envisage. In order to make the training sustainable, each local government should secure the budget according to their training plan

# Relevant issues of ICGIAP

## Areas of Activity 	Capacity Development Unit (CDU) established and formulated training program

Establishment of CDU 	There are always needs of training to   improve the capacity of the elected representative, officers and staffs of the city corporation. In order to make comprehensive training program and sustain it, Capacity Development Unit (CDU) is established in the city corporation.

## Tasks of CDU

:

Task1		: CDU is formed and approved by City Corporation Meeting

Task 2		: Letter is issued by Mayor and circulates it to the members

Task 3		: Hold workshop on CDU operation

Task 4	: Formulate Program for technical training and Kaizen activities with budget plan

Task 5		: Conduct the technical training according to schedule

Task 6		: Produce report on capacity development

## Composition of CDU

CEO 				Chairperson

Secretary 			Member Secretary

Head of all department 		Member

## ToR of CDU

- CDU initiate formulating skill training program based on ARP and ICGIAP

- CDU proposes skill training course and Kaizen training with budget plan

- CDU organize training provider, and arrange training course by the CCs own fund

- Facilitate Kaizen training and activities

- Monitor implementation of Kaizen activities and technical training

- Assess capacity or work improved by Kaizen and technical training

- Prepare progress (quarterly) and final report on capacity development activities

## Action by

- Secretary

## Time Schedule

Task 1-3 by mid of 1st year

Task 4 by end of 1st year

Task 5 every year from 2nd year

Task 6 end of every fiscal year

.

## Indicators

#### 1st Performance Review: Training program formulated

Training program should be formulated by the 1st performance review. The training program should be formulated based on Administrative Reform Plan reviewed by ARC. The contents of training program should be relevant to ARP and feasible in terms of financial capacity. The format for training program is given in this guideline. CGP will not provide fund for the training program apart from the training specially arranged by CGP, thus it should be implemented by CC’s own budget, or CCs may look for fund from other sources.

#### 2nd Performance Review: Report on capacity development produced by CDU

As it is described in this guideline, CDU is supposed to produce quarterly and annual report. CDU should produce these report based on the formats which is given in this guideline.

# Objectives

## Objectives

Capacity Development Unit (CDU) is proposed to establish as institutional settings to develop the training program for sustainable capacity development of CC. CDU consists of top management officers, such as, CEO, secretary and other heads of department. It will analyze the needs of training based on ARP. It will formulate technical training with training providers, such as, NILG, LGED, DPHE, private institutes, NGOs and so on. It will also promote Kaizen activities. At the end of the fiscal year, it will evaluate training activities and performance of officials who received the training.

# Relevant Organizations, Stakeholders and their role

## PCO/PIU

Project Coordination Office (PCO) and Project Implementation Unit (PIU) are responsible for facilitation and monitoring of CDU. PIU will make budget for CDU activities based on proposed training program, and submit it to the relevant standing committee.

## Training providers

There are several training providers. CDU is responsible for making contact with them and outsource training activity. If the budget of CC will not allow them to conduct training program, then CDU organize training by CC’s own human resources. In other words, senior officials give training to junior officials. CDU coordinates with trainers, make schedule and budget for each training. Annex I shows potential training providers and subjects of training they can provide. CCs may look for other providers which are available in the CC or national level according to their needs. NILG is one of training provider, but it has wider network with resource persons and institutions, thus it is recommended that CC consults with NILG at the initial stage. The Municipal Support Unit of Urban Management Unit (UMU) of LGED is also one of the training providers in Bangladesh.

## Administrative Reform Committee

ARC has authority to request CDU to formulate training program. CDU formulate training program based on ARP, but prioritization of training should follow the strategic plan produced by ARC.

# Necessary Tasks and Procedure

## Formulation of CDU

Member of CDU is recommended as follow;

- CEO – Chairperson

- Secretary – Member secretary

- Heads of all dept. – Member

CDU is formed by CEO, and approved by City Council meeting. The official letter should be prepared by Mayor and circulated.

## Orientation workshop

Project Coordination Office (PCO) will organize orientation workshop on CDU formulation and operation in each CC. Orientation workshop is to explain the concept of CDU, functions and schedule of activities. It should be held immediately after ICGP consultant starts working on the ground. ICGP consultant will prepare materials for workshop, and organize workshop. ICGP consultant will give lecture on the concept of CDU and operational procedures.

## Formulation procedure of training program

Training program will be formulated as per the following steps:

#### Step 1: review of ARP

ARP is given to every CC. ARP describes “present status (1st sheet), “5 years action plan (2nd Sheet” and “Administrative Reform Plan (the last sheet)”. Each department confirms “Responsible Dept./Sec. in “present status”. Then, review “Reason for Moderate or Low performance”, “Present status” and “5 year action plan” in the second sheet namely “5 year action plan”. Finally, reviews “applicable activity” in ARP (3rd sheet) that show the actions to be taken, such as, “Kaizen activity”, Technology transfer”, “Installment of equipment” and “Increase of manpower”.

Please remember that review of ARP will be requested to head of departments by ARC. Thus, CDU does not have to request, but to guide and monitor the progress of review activity.

#### Step 2: Proposal for training, installation of equipment and Increase of manpower

For every function, relevant activity is recommended in ARP. Each department will select one or two activities from “technology transfer”, “installation of equipment” and “increase of manpower” that can help improve services of the departments. Each department fill in necessary information in the summary sheet (Annex II, example of inputs are given in the format), and accordingly, prepare detailed plan for training, equipment installation and recruitment of manpower based on the format (Annex III).

#### Step 3: Selection and formulation of Capacity Development Program

CDU compiles summary sheet prepared by the departments into one summary sheet. It also reviews contents of training proposals and give marks according to criteria listed below. Once the training are prioritized based on given total budget for Capacity Development Program, CDU compile the selected proposals and total budget, and make proposal as Capacity Development program according to the format (Annex IV).

Selection Criteria will include the following:

- Urgency: Is improvement of service delivery urgent?

- Relevance: Is the proposal relevant to vision and mission of department or vision of CC? Does increase of manpower (permanent staff) follow approved organogram? If not, is it part-time?

- Effectiveness: Is the proposal help achieve target of 5 year action plan in ARP?

- Efficiency: is it cost-effective? Compare expenditure and impact. Is proposed budget realistic or affordable for CC?

- Impact: How much does training have impact on public services? Is it measurable?

- Sustainability: Does the training, equipment or manpower sustain improved public services?

Note 1: There is a table for evaluation of proposal. CDU members marks proposal according to the criteria. The total marks of proposal can be used for prioritization of proposed training.

Note 2: After the selection of activities, if any necessary modifications, such as, target officials/councilors, number of participants, contents of training, budget, then CDU advises responsible departments to revise the proposal for finalization.

#### Kaizen Training

Kaizen training should be implemented following the guideline for Kaizen Activity.

## Schedule and Monitoring of Activity

Detailed schedule of training, equipment installation and recruitment will be given in the proposals prepared by each department. CDU compiles the schedule in the given format (Annex V). It also monitors the activities quarterly according to the schedule.

## Assessment of Capacity Development Program

Assessment of each training activity should be done by the trainer immediately after the training activity, and assessment report should be prepared based on the format (Annex VI). The format for assessment can be modified according to the nature of training activity. CDU makes sure to include assessment of training in the TOR of trainer.

## Quarterly and final report on CDU activity

Quarterly report will be made based on the format (Annex VII). For the final report, CDU uses the format which is same as quarterly report. It is just a sample for report writing which shows minimum information, thus it can be modified by CDU.

# Implementation Schedule

## Formation of CDU

CDU is formed soon after the issue of letter from PCO

## Formulation of Capacity Development Program

Formulation of Capacity Development Program with budget should be done by June, 2015.

## Monitoring

Implementation of the Program will start with fiscal year of 2015-16. CDU conducts monitoring work according to the Schedule and Monitoring Sheet. Some of training, equipment procurement and recruitment of manpower concerning ICGP could be done immediately after the start of ICGP.

## Assessment

Assessment of each activity should be done within one month after the activity.

## Reports

Quarterly report should be prepared by end of each quarter, namely, end of September, December, March, and the report of the last quarter is substituted by final report.

Final report should be prepared by end of June.

See detail of implementation schedule in annex VIII

- List of Training Provider

| List of Training Provider |  |  |
| --- | --- | --- |
| No. | Training Provider | Training Contents |
| GoB |  |  |
| 1 | NILG | Kaizen, general public administration, office management |
| 2 | LGED | Civil engineering in general, quality control of civil engineering, e-GP, Master Plan, Sector planning, fry over, |
| 3 | Urban Management Unit (UMU) |  |
| 4 | DPHE | Water supply, water quality control, slum development |
| 5 | BARD (Comilla) RDA (Bogra) | Community mobilization, facilitation, participatory development, income generation for women, gender issue |
| 6 | Dept. of Social Welfare | Poverty reduction, gender issue |
| 7 | Other City Corporations | Any kind of functions of City Corporation, such as waste collection, |
| 8 | Department of Environment | Any kind of environmental issue |
| Academic Institutions |  |  |
| 1 | Institute of Governance Studies, RRAC University | Governance, environment governance, private sector development, budget planning based on policy, democracy, negotiation and conflict management |
| 2 | BUET/CUET/Other universities | Urban planning, Civil Engineer, Sector plan, Waste management |
| NGOs/International Organizations |  |  |
| 1 | IUCN Bangladesh | Environmental conservation |
| 2 | Bangladesh Environmental Lawyers Association | Environmental laws and regulations |
| 3 | Institution of Engineers Bangladesh (IEB) |  |
| 4 | Bangladesh Institute of Management (BIM) | Management Capacity Building |
| 5 | Bangladesh Institute of Administrative Management (BIAM) | Development, Administration and Management |

- Summary Sheet for Capacity Development Program

Summary Sheet for Capacity Development Program

| No. | Dept. / Section | Concerning Function | Activity (training / equipment / manpower9 | Target Officers /Councilors | No. of Input (participants) | Training Duration (days) | Duration (dd/mm-dd/mm) | Contents of Training / Equipment / Responsibilities of Employee | Training Institutions / Experts | Estimated Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Conservancy Dept. | 1-1. Responsibilities for sanitation | Increase of sanitation inspector | N/A | 3 | N/A | permanent | Field level inspection of sanitary situation in primary waste collection points and dumping site | N/A | 30,000Tk/month x 12 months / year = 360,000 / year x 3 persons |
| 2 | Conservancy Dept. | 1.4-7. Removal, collection and disposal of waste | Training on waste collection and disposal at primary collection site | Cleaner (waste collection) | 30 | 2days | 01/Aug-30/Sep | Route and schedule of waste collection Dumping at primary collection site Cleaning of dumping site | Sanitary Inspector | 300Tk x 2 days x 30 person = 18,000Tk |
| 3 | Conservancy Dept. | 1.4-7. Removal, collection and disposal of waste | Installment of trolley and dustbins | N/A | 30 trolley 300 dustbins | N/A | 01/Aug-30/Sep | 500 litter trolley with rickshaw 100 litter dust bin | N/A | 50,000Tk x 30 =1500,000 5,000Tk x 300 = 1500,000 |
| 4 | Conservancy Dept. | 1.4-7. Removal, collection and disposal of waste | Collect waste from primary collection point or dust bin and transport to dumping site | Medical officer / Sanitary Inspectors | 5 | 3 days | 01/Sep-30/Oct | How to make collecting schedule How to manage dust bin How to transport waste from primary collection point to dumping site | Dhaka CC, Conservancy Dept. | 5,000Tk x 3 days x 2 officials = 30,000Tk |
| 5 |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |  |

- Format for Proposal for Capacity Development Program

Capacity Development Program

Proposal for Capacity Development Activity

on

[specific item]

XXX Department, XXX Section

XXX Standing Committee

Name of Head of department/Standing Committee

Date: DD/MM/20XX

XXXX City Corporation

1. Title of Capacity Development Activity

2. Justifications

Describe background of training, equipment installation, increase of manpower such as problem of service delivery, shortage of manpower, lack of skills, equipment and so on. Logically explain how problem in service delivery is related to the lack of skills which will be improved through the proposed training.

3. Objectives and Target

3.1 Objectives

Explain main objectives of training, equipment installation and increase of manpower

3.2 Specific Target

Explain what ability participants or department can improve by training, installation of equipment or increase of manpower as bullets

1.

2.

3.

4. Impact

How this training, equipment installation and increase of manpower help improve service delivery.

5. Cost of Training

| No. | Items of Training / equipment / manpower | Detail training contents, specification of equipment, responsibility of manpower |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |

6. Provider of Training / Equipment

Explain brief profile of institutions and company which can provide trainings and equipment.

7. Training Schedule

Date, duration, time schedule of training, equipment installation and recruitment of manpower

| Detail Activity | Month |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Sep | Oct | Nov | Dec | Jan | Feb |

8. Budget of Training

Training fee / honorarium for training provider / trainer

Training facilities (rent of room or hall, projector and screen, PC, tea, meals, etc.)

Training materials

Number of equipment, unit cost

Monthly salary and honorarium, number of manpower, duration of recruitment (if, it is permanent staff, then propose annual expenditure for each staff)

CDU member use

Evaluation of Proposal

| Evaluation Items | High | Moderate | Low | Score | Remarks |
| --- | --- | --- | --- | --- | --- |
| Urgency |  |  |  |  |  |
| Relevance |  |  |  |  |  |
| Effectiveness |  |  |  |  |  |
| Efficiency |  |  |  |  |  |
| Impact |  |  |  |  |  |
| Sustainability |  |  |  |  |  |

Score: High=3, Moderate=2, Low=1

- Format for Proposal for Training Activity

Proposal for Training

Activity

In 20XX

Capacity Development Unit (CDU)

Name of Head of CDU

Date: DD/MM/20XX

XXXX City Corporation

1. Justification

In order to maintain accountability of capacity development program, explain background to conduct capacity development activity. Explain why CC needs to provide trainings, install equipment and recruit manpower. The explanations should be understandable for tax payers. Describe justification of selected training, equipment installation, increase of manpower based on vision and mission of CC, needs of people and problems of service delivery. Logically explain how problem in service delivery is related to the lack of skills which will be improved through the proposed training.

2. Objectives

Explain how selected trainings, equipment installation and increase of manpower can help achieve vision and mission of CC.

3. Contents of Capacity Development Program

| No. | Items of Training / equipment / manpower | Detail training contents, specification of equipment, responsibility of manpower | Score of Evaluation |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |

Note: See Annex I, proposals for capacity development activities (attach proposals of selected activities)

4. Training Schedule

Schedule of capacity development activities are described in the Annex IV (Attach training schedule and monitoring sheet)

5. Budget of Training

| No. | Name of Activity | Item of Expenditure | Unit Cost | No. | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Increase of sanitation inspector | Salary | 360,000 | 3 | 1,080,000 |
|  |  | Sub total |  |  | 1,080,000 |
| 2 | Training on waste collection and disposal at primary collection site | Honorarium for participants | 600 | 30 | 18,000 |
|  |  | Training facilities | 50 | 30 | 1,500 |
|  |  | Sub total |  |  | 19,500 |
| 3 | Installment of Trolley and dustbins | Trolley | 50,000 | 30 | 1,500,000 |
|  |  | Dust bin | 5,000 | 300 | 1,500,000 |
|  |  | Distribution and installation cost | 50 | 300 | 15,000 |
|  |  | Sub total |  |  | 3,015,000 |
| 4 | Collect waste from primary collection point or dust bin and transport to dumping site | Training fee | 15,000 | 2 | 30,000 |
|  |  | Training facilities | 100 | 21 | 2,100 |
|  |  | Sub total |  |  | 32,100 |
|  |  | Grand Total |  |  | 4,146,600 |

- Schedule of Capacity Development Program and Monitoring Sheet

| Schedule of Capacity Development Program and Monitoring Sheet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Activity / Milestone | Responsible Officer | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |
| 1 | Increase of Sanitation Inspector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Prepare recruitment notice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Open notice on newspapers and other media |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Screening of application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Interview of selected candidates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final interview with candidates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Recruitment procedure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Training on waste collection and disposal at primary collection site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Selection of trainers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preparatory discussion with trainers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make detail training contents and schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make report on training activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Installment of trolley and dust bins |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make specifications of trolley and dust bin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make tender documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Tender for procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Selection of supplier |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Installment or distribution of trolley and bins |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Collect waste from primary collection point or dust bin and transport to dumping site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Selection of trainers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preparatory discussion with trainers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make detail training contents and schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Make report on training activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Format for Assessment for Capacity Development Activity

Assessment for Capacity Development Activity

1. Title of Activity:

2. Duration: DD/MM/-DD/MM/20XX

3. Schedule of Capacity Development Activity

Describe actual schedule, if it is different from proposed schedule

Copy paste the schedule on proposal, if it is done as proposed

4. Number of Participants / Equipment installed / Manpower recruited

| Target | Actual |
| --- | --- |

5. Achievements

(1) Targets and Achievement

| No. | Targets | Achievements |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |

Describe targets which are mentioned in the proposal, and explain achievement after the implementation of activity.

(2) Result of Questionnaire (only for training activity)

| Questions |  | Options |  | No. of Answer |
| --- | --- | --- | --- | --- |
| 1- | Do you find the training subject useful for you? | a | useful |  |
|  |  | b | some |  |
|  |  | c | not useful |  |
| 2- | Have you participated in a training on same subject? | a | yes |  |
|  |  | b | No |  |
|  | If yes, which training was more useful for you? | a | This training |  |
|  |  | b | Previous training |  |
| 3- | How were the content of the training? | a | sufficient |  |
|  |  | b | insufficient |  |
|  |  | c | poor |  |
| 4- | How do you find the training text | a | sufficient |  |
|  |  | b | insufficient |  |
|  |  | c | poor |  |
| 5- | How was the time allocation? | a | appropriate |  |
|  |  | b | need to be longer |  |
|  |  | c | need to be shorter |  |
| 6- | How was the timing of training? | a | appropriate |  |
|  |  | b | not appropriate |  |
| 7- | How was the place of the training course? | a | appropriate |  |
|  |  | b | not appropriate |  |
| 8- | How do you evaluate the lecturer (trainer)? | a | appropriate |  |
|  |  | b | not appropriate |  |
| 9- | How do you evaluate the training arrangement? | a | appropriate |  |
|  |  | b | not appropriate |  |
| 10- | Do you want to apply the process on the ground? | a | yes |  |
|  |  | b | no |  |

6. Budget

| Proposed | Actual |
| --- | --- |

7. Way Forward

- Format for Quarterly Report

Quarterly Report

Capacity Development Program

Capacity Development Unit, XXX City Corpotation

1. Summary of Achievements

Describe the achievements

2. Summary Sheet of Training Program

| No. | Implemented Training | Proposed Input (participants / equipment / manpower) | Actual Input (participants / equipment / manpower) | Proposed Target | Achievements | Proposed Budget | Actual Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Increase of sanitation inspector | 3 Sanitary Inspector | 3 Sanitary Inspector | 1. 2. 3. | 1. 2. 3. |  |  |
| 2 | Training on waste collection and disposal at primary collection site | 30 participants | 25 participants | 1. 2. 3. | 1. 2. 3. |  |  |
| 3 | Installment of trolley and dustbins | trolley 30 Dust bin 300 | trolley 40 Dust bin 350 | 1. 2. 3. | 1. 2. 3. |  |  |

3. Challenges

Explain any challenges if any activities are behind the schedule

- Implementation Schedule

- Sample Budget for implementation of the CDU

| City Governance Project Annex-09 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Capacity Development Unit |  |  |  |  |  |  |  |  |  |  |  |
| Tentative Budget for implementation of Capacity Development Unit (2014-2015) |  |  |  |  |  |  |  |  |  |  |  |
| Sl | Name Of Activity | Activity Details | Unit/Batch/Days | Unit Cost (tk) | Total Amount | Responsible Person | Time Frame |  |  |  | Remarks |
|  |  |  |  |  |  |  | 1st Qrt | 2nd Qrt | 3rd Qrt | 4th Qrt |  |
| 1 | Orientation Workshop on CDU ( Non Residential) |  |  |  |  |  |  |  |  |  |  |
|  | One day Orientation workshop on CDU formulation and operation at CC level | 25 Officials/Staffs from different dept. 3 officials from PCO, 5 CGP staff, 2 support staff ; Total 35 persons |  |  |  | CC |  |  |  |  |  |
|  | Food | Two times snacks and Tea for 35 Person for 1 Day | 35 | 60 | 2100 | CC |  |  |  |  |  |
|  |  | Lunch-200/Person*32 | 35 | 200 | 7000 | CC |  |  |  |  |  |
|  | Logistics | Note pad,Pen, Printing Materials, VIPP Card, Poster Paper, Marker etc ; 30/ Person | 33 | 50 | 1650 | CC |  |  |  |  |  |
|  | Convance for Participants/ Honourium | 300tk/ person for 25 person for 1 Day | 25 | 300 | 7500 | CC |  |  |  |  |  |
|  | Sub Total= |  |  |  | 18250 |  |  |  |  |  |  |
| 2 | Workshop on formulation of training program |  |  |  |  |  |  |  |  |  |  |
|  | Two days workshop on formulationof training program at CC level | 25 Officials/Staffs from different dept., 5 CGP staff, 2 support staff ; Total 32 persons |  |  |  | CC |  |  |  |  |  |
|  | Food | Four times snacks and Tea for 32 Person for 2 Days | 32 | 120 | 3840 | CC |  |  |  |  |  |
|  |  | Lunch-200/Person*32 for 2 days | 32 | 400 | 12800 | CC |  |  |  |  |  |
|  | Logistics | Note pad,Pen, Printing Materials, VIPP Card, Poster Paper, Marker etc ; 30/ Person | 30 | 50 | 1500 | CC |  |  |  |  |  |
|  | Convance for Participants/ Honourium | 300tk/ person for 25 person for 2 Days | 25 | 600 | 15000 | CC |  |  |  |  |  |
|  | Sub Total= |  |  |  | 33140 |  |  |  |  |  |  |
|  | Total Approximate Budget for CCs = |  |  |  | 51390 |  |  |  |  |  |  |